## Meeting Outcomes & Summary (hidden)
Rainbow Hospitals – Final TCO (30-Apr-2026 — v1.3, PDF-validated + AA recon) ¦ Primary: Hyderabad ¦ DR: Mumbai
Primary: Hyderabad (ap-south-2) ¦ DR: Mumbai (ap-south-1) Multi-Region Active-Passive
✅ Confirmed Decisions from Chari Meeting (22-Apr-2026)
1. SAP Strategy: SAP servers hosted by 3rd party vendor (HANA upgrade ongoing)
BUT: Chari clarified — 'Old ECC data everything should be moved to AWS' → SAP apps included as-is
2. Primary DC: Hyderabad (ap-south-2) — active production
3. DR: Mumbai (ap-south-1) — Multi-Region Active-Passive with continuous replication
4. Chari requested quotes for BOTH Active-Active AND Active-Passive options
5. HIS: Lift-and-shift approach. Legacy HIS servers NOT migrated (decommission on-prem)
6. MongoDB: AWS Marketplace-based deployment agreed
7. Licensing: AWS License Included for Windows + SQL Server (no BYOL)
8. Biometric, Blood Bank → Windows SQL stays (Linux SQL not feasible immediately)
9. Security: AWS Inspector replaces EDR ¦ AWS Backup replaces CommVault ¦ Palo Alto via Marketplace
10. Graviton/ARM: To be explored — Chari checking HIS application compatibility
11. S3 + CloudFront: Evaluate for static/web workloads
12. Existing AWS workloads: Will MOVE to Hyderabad during mobilise phase (Phase 2)
🔴 CRITICAL CORRECTIONS IN THIS VERSION — HYDERABAD INSTANCE AVAILABILITY
⚠️ T3a NOT available in HYD. c6a.6xlarge DOES NOT EXIST as instance type (no 6xl in C-series).
⚠️ M7i (Intel) also NOT AVAILABLE in Hyderabad — already using M6i (validated earlier)
Validated Instance Replacements:
• RNBWHYDFDBK (Feedback Non-Prod): t3a.medium → t3.medium (Intel Windows burstable)
• RainbowC52431 (ICU Ubuntu Non-Prod): t3a.xlarge → t3.xlarge (Intel, Graviton pending Chari)
• BIUAT-MIS (BI UAT Ubuntu): t3a.xlarge → t3.xlarge (Intel, Graviton pending Chari)
• Manage_Engine (ME Windows): t3a.2xlarge → t3.2xlarge (Intel Windows)
• Existing HMS DEPLOYSERV01: t3a.small → t3.small (Intel, Graviton pending Chari)
• newserver-26-08-2025 + New-server-replica (Windows): t3a.xlarge → t3.xlarge (Intel)
✅ Validated AWS Services Available in Hyderabad (ap-south-2)
EC2 Instances: M6a, M6i, R6i, R6a, R7i, C6a, C6i, T3, T4g — confirmed available
Supporting Services: EBS, VPC, NAT, ELB, S3, RDS, Redshift, CloudWatch, CloudTrail
Security: GuardDuty, Security Hub, WAF, Config, AWS Inspector, KMS
DR: AWS DRS (cross-region to Mumbai), AWS Backup, S3 CRR
Marketplace: Palo Alto VM-Series, MongoDB Atlas (launched HYD in March 2025)
Global: Route 53, KMS, AWS Marketplace — always available
🔄 OTHER CHANGES APPLIED IN THIS VERSION (vs 23-Apr)
• Existing HMS workloads moved from Mumbai to Hyderabad (Phase 2 mobilise)
• Active-Passive DR uses AWS DRS continuous replication (7 CtrlS + 10 HMS)
• MongoDB Atlas ADDED via AWS Marketplace (Hyderabad primary + Mumbai DR)
• Palo Alto VM-Series ADDED via AWS Marketplace (HA pair both regions)
• AWS Inspector ADDED for both Hyderabad + Mumbai regions
• SAP_PI_PRD_New corrected (was t3.nano typo → m6i.4xlarge)
• RCHSOLMAN72 corrected (AMD → Intel for SAP embedded HANA cert)
• mobileapp DR corrected (Windows → Ubuntu to match primary)
• Rainbow_MRD right-sized (c6a.8xlarge → c6a.6xlarge exact match)
• EBS headroom added to 7 servers at 85-90% disk utilisation
📊 Utilisation Data Analysis (From Customer PPT)
• Disk utilisation provided — HIGH across estate (79-99%). Headroom added where needed.
• CPU/RAM utilisation data NOT PROVIDED — sizing based on current allocated specs
• Recommendation: 2-week CloudWatch observation post-migration for further right-sizing
⚠️ Open Items / Action Points
1. Active-Active quote alongside Active-Passive — see comparison sheet
2. Graviton compatibility for HIS — Chari coming back. T4g successfully used for Ubuntu UAT
3. SAP integration with HIS — confirmed, details pending
4. Palo Alto BYOL license — get quote from Rahul (Minfy)
5. MongoDB Atlas multi-region DR confirmation with Chari
6. 2 unknown Windows servers (newserver-26-08-2025) — confirm purpose
7. SAP HANA r6i.2xlarge is below SAP cert threshold — discuss with Chari
📝 Changes in v1.2 (30-Apr-2026) — PDF Validation Pass
• Validated against AWS Pricing Calculator export dated 30-Apr-2026 (AWS-TCO-30April.pdf).
• Primary TCO Hyderabad: 7 EBS allocations corrected; SAP-DevTesting instance updated m6a.2xlarge → r6i.xlarge per AWS Calculator. Total $/mo unchanged at $12,450.43.
• DR TCO Mumbai: RAINDC03 DR instance label corrected m6i.large → m6i.xlarge (cost was already correct at $226.67). Total unchanged at $8,281.29.
• SuppServices4ExistingHIS: VPC HYD $271.14 → $329.83; VPC Mumbai DR $137.76 → $329.83; Inter-region DT $192.07 → $176.13; added S3 DR (Mumbai 2TB CRR) $56.60. Net total change: $3,657.05 → $3,948.48 (+$291.43).
• Marketplace Offerings: validated within $0.38 rounding tolerance, no edits.
• Existing AWS HMS Phase 2: DEPLOYSERV01 $10.13 → $10.87; Grafana Monitoring $71.21 → $63.32. Net total change: $6,216.29 → $6,209.14 (-$7.15). Region typo at CloudWatch DR row corrected (0 → Mumbai).
• Consolidated Master View, Consolidated Summary, Master KareXpert, Master MyHealthcare: re-pointed Supporting Services reference from 'Supporting Services'!F28 → 'SuppServices4ExistingHIS'!F29 (PDF-validated source).
• Active-Active vs Passive: DR Supporting Services SUMPRODUCT re-pointed to SuppServices4ExistingHIS for consistency.
• 'Supporting Services' sheet (with Logically Air-Gapped Vault row added in v1.1) is preserved as a separate scenario sheet but is no longer referenced by consolidated views — calculator-validated baseline is the source of truth in v1.2.
📝 Changes in v1.3 (30-Apr-2026) — Active-Active Supporting Services Reconciliation
• Active-Active vs Passive sheet: AA Mumbai supporting services updated to reflect v1.2 PDF validation and correct internal inconsistencies.
• VPC + NAT Gateway (AA Mumbai): $271.14 → $329.83 (matches updated HYD per PDF).
• Security Hub (AA Mumbai): $85 → $85.01 (matches updated HYD per PDF).
• AWS Backup (AA Mumbai): $268.55 → $391.78 (full primary backup, matches HYD per PDF). Previous value was incorrectly lower than even AP DR CRR backup ($295.62).
• Inter-region Data Transfer (AA): $120 → $176.13 (set to AP value as floor; AA bidirectional traffic likely exceeds this — to be validated separately).
• Data Transfer Egress (AA Mumbai): $234.25 → $303.25 (combined intra+inbound+egress, matching active-region HYD per PDF).
• AA Mumbai supporting total: $1,505.24 → $1,812.30 (+$307.06).
• AA total DR cost: $12,818.24 → $13,125.30. Active-Active is now correctly higher than Active-Passive on like-for-like services (the residual lower AA total versus AP total reflects only that AA does not require AWS DRS at $1,191.28).

## Master - KareXpert Option
Rainbow Hospitals — Complete TCO with KareXpert Option
Primary: Hyderabad ¦ DR: Mumbai Active-Passive ¦ HIS vendor-specific costs added
| Category | Monthly (USD) | Annual (USD) | Notes
| ControlS - Production Servers (CSP 3yr) | 10962.73 | 131552.76 | Existing ControlS migration servers.
| ControlS - Non-Prod Servers (OD best) | 1387.59 | 16651.08 | Cheaper of 75% util or 8hr/day.
| DR - Mumbai (Active-Passive) | 8281.29 | 99375.48 | 10 critical servers pilot-light.
| Supporting Services (HYD + Mumbai) | 3948.48 | 47381.76 | Inspector, Backup 365d, WAF, DRS.
| Marketplace (Palo Alto + MongoDB) | 5173.08 | 62076.96 | Palo Alto HA + MongoDB Atlas.
| Existing AWS HMS (Phase 2) | 6209.14 | 74509.68 | Moving Mumbai → HYD + DR Mumbai.
| NEW HIS — KareXpert Option | 4768.17 | 57218.04 | See 'HIS BOM - KareXpert' sheet for detail.
| GRAND TOTAL (KareXpert Option) | 40730.48 | 488765.76 | Complete Rainbow AWS Landscape
HIS Vendor Cost Comparison
MyHealthcare (MHEA): $8,382.62/mo (214 Graviton VMs, microservices on EC2)
KareXpert: $4,768.17/mo (24 EKS worker nodes, Kubernetes-based)
Difference: $3,614.45/mo ($43,373.40/yr)
⚠️ All HIS EC2 rates are estimates — validate in AWS Pricing Calculator before submission.
⚠️ KareXpert MongoDB M60 may REPLACE existing Atlas clusters — clarify with vendor.
KareXpert DR Rough 1,500 to 2,500 USD per month

## Master - MyHealthcare Option
Rainbow Hospitals — Complete TCO with MyHealthcare Option
Primary: Hyderabad ¦ DR: Mumbai Active-Passive ¦ HIS vendor-specific costs added
| Category | Monthly (USD) | Annual (USD) | Notes
| ControlS - Production Servers (CSP 3yr) | 10962.73 | 131552.76 | Existing ControlS migration servers.
| ControlS - Non-Prod Servers (OD best) | 1387.59 | 16651.08 | Cheaper of 75% util or 8hr/day.
| DR - Mumbai (Active-Passive) | 8281.29 | 99375.48 | 10 critical servers pilot-light.
| Supporting Services (HYD + Mumbai) | 3948.48 | 47381.76 | Inspector, Backup 365d, WAF, DRS.
| Marketplace (Palo Alto + MongoDB) | 5173.08 | 62076.96 | Palo Alto HA + MongoDB Atlas.
| Existing AWS HMS (Phase 2) | 6209.14 | 74509.68 | Moving Mumbai → HYD + DR Mumbai.
| NEW HIS — MyHealthcare Option | 8382.62 | 100591.44 | See 'HIS BOM - MyHealthcare' sheet for detail.
| GRAND TOTAL (MyHealthcare Option) | 44344.93 | 532139.16 | Complete Rainbow AWS Landscape
HIS Vendor Cost Comparison
MyHealthcare (MHEA): $8,382.62/mo (214 Graviton VMs, microservices on EC2)
KareXpert: $4,768.17/mo (24 EKS worker nodes, Kubernetes-based)
Difference: $3,614.45/mo ($43,373.40/yr)
⚠️ All HIS EC2 rates are estimates — validate in AWS Pricing Calculator before submission.
⚠️ KareXpert MongoDB M60 may REPLACE existing Atlas clusters — clarify with vendor.
MyHealthcare DR rough estimate 3,000 to 4,000 USD per month

## MyHealthCommercial Breakdown
Breakup | Annual Cost
Cntrl S Infra | 148203.84 |  |  |  | MAP Credits
DR | 99375.48 |  |  |  | Cntrl S Infra | 148203.84
Shared Services | 47381.76 |  |  |  | DR | 99375.48
Marketplace | 62076.96 |  |  |  | Shared Services | 47381.76
Existing HIS | 74509.68 | Existing application resources will get optimized only snapshot will be there. |  |  | MyHealthcare | 100591.44
MyHealthcare | 100591.44 |  |  |  | MyHealthcare DR (approx) $4,000 MRR | 48000
MyHealthcare DR (approx) $4,000 MRR | 48000
Total Cost (Existing + Cntrl S + DR + Marketplace + ) | 580139.16 |  |  |  | Total ARR | 443552.52
Total MAP Credits | 104654.178
Minfy Discount | 15541.866
Total Effective Cost Year 1 | 459943.116
MS Charges | 51806.22
Total TCO Including MS Year 1 with Marketplace | 511749.336
Total Effective Cost Year 1 Without Marketplace (SaaS - MongoDB + PaloAlto) | 449672.376
Note - No Discount/Credits will be applied on Marketplace
Note: Optimize the Existing HIS running in AWS, only the snapshots will be there.
MAP Credits | 66532.878 |  | 3294.85 | 39538.2
SAP Credits | 31000.5 |  | 1871.9 | 22462.8
Windows | 7120.8 |  | SAP | 62001
| 104654.178 | windows | 3295 | 39540
|  |  | 2639 | 31668
71208
7120.8

## KareXpeCommercial Breakdown
Breakup | Annual Cost
Cntrl S Infra | 148203.84
DR | 99375.48
Shared Services | 47381.76 |  | MAP Credits
Marketplace | 62076.96 |  | Cntrl S Infra | 148203.84 | 3294.85 | 39538.2
Existing AWS HIS | 74509.68 | Existing application resources will get optimized only snapshot will be there. | DR | 99375.48 | 1871.9 | 22462.8
KareXpert | 57218.04 |  | Shared Services | 47381.76 | SAP Total ARR | 62001
KareXpert DR (Approx) - $2,500 / MRR | 30000 |  | KareExpert | 57218.04
Total Cost (Existing + Cntrl S + DR + Marketplace + New HIS) | 518765.76 |  | KareExpert DR | 30000
|  |  | Total | 382179.12 | 3295 | 39540
Total MAP Credits | 95448.168 |  |  |  | 2639 | 31668
Minfy Discount | 13700.664 |  |  |  |  | 71208
AWS Total Effective Cost for Year 1 | 409616.928 |  |  |  | Total Win | 7120.8
Minfy MS Cost | 45668.88
Total TCO Including MS Year 1 with Marketplace | 455285.808
Total Effective Cost Year 1 Without Marketplace (SaaS - MongoDB + PaloAlto) | 393208.848
Note - No Discount/Credits will be applied on Marketplace
Note: Optimize the Existing HIS running in AWS, only the snapshots will be there.
MAP Credits | 57326.868
SAP Credits | 31000.5
Windows | 7120.8
| 95448.168 | windows

## Commercial Breakdown
Breakup | Annual Cost
Cntrl S Infra | 148203.84
DR | 99375.48
Shared Services | 47381.76
Marketplace | 62076.96
AD&PACS | 0
Existing AWS | 74509.68
Total Cost (Existing + Cntrl S + DR + Marketplace + AD&PACS) | 431547.72
Total MAP Credits | 93541.914
Minfy Discount | 11084.1228
Total Effective Cost Year 1 | 326921.6832
Total Effective Cost Year 1 Without Marketplace (SaaS - MongoDB + PaloAlto) | 369470.76
Note - No Discount/Credits will be applied on Marketplace
MAP Credits | 55420.614 |  | 3294.85 | 39538.2
SAP Credits | 31000.5 |  | 1871.9 | 22462.8
DA | 7120.8 |  | SAP | 62001
| 93541.914 | windows | 3295 | 39540
|  |  | 2639 | 31668
71208
7120.8

## Consolidated Master View
Rainbow Hospitals — Consolidated Master Pricing View (30-Apr-2026 — v1.3)
All EC2 prices validated against AWS Pricing Calculator export (24-Apr-2026). Filter 'Hosting Environment' for split views.
S.No | Server / Service | Hosting Env | Category | Region | Instance | Monthly (USD) | Annual (USD) | Scope | Notes
CtrlS PRODUCTION (PDF Validated)
1 | RAINDC03 | CtrlS → AWS | EC2 - Prod | Hyderabad | m6i.xlarge | 226.67 | 2720.04 | In Scope | AD Primary DC
2 | RAINDC02 | CtrlS → AWS | EC2 - Prod | Hyderabad | m6i.xlarge | 226.67 | 2720.04 | In Scope | AD Secondary DC
3 | Rchbbserver | CtrlS → AWS | EC2 - Prod | Hyderabad | m6a.4xlarge | 2193.63 | 26323.56 | In Scope | Blood Bank + SQL Std
4 | Rainbow_MRD | CtrlS → AWS | EC2 - Prod | Hyderabad | c6a.8xlarge | 2270.91 | 27250.92 | In Scope | MRD OCR
5 | RCHAEON | CtrlS → AWS | EC2 - Prod | Hyderabad | r6a.4xlarge | 2301.86 | 27622.32 | In Scope | Biometric + SQL Std
6 | RainbowRPA | CtrlS → AWS | EC2 - Prod | Hyderabad | m6a.2xlarge | 382.08 | 4584.96 | In Scope | RPA Reporting
7 | SAP_PI_PRD | CtrlS → AWS | EC2 - Prod (SAP) | Hyderabad | m6a.4xlarge | 830.11 | 9961.32 | In Scope | SAP PI/PO
8 | repsapGRP | CtrlS → AWS | EC2 - Prod (SAP) | Hyderabad | r6a.2xlarge | 598.01 | 7176.12 | In Scope | SAP ECC Node A (was HANA)
9 | repsapAPP | CtrlS → AWS | EC2 - Prod (SAP) | Hyderabad | r6a.2xlarge | 479.45 | 5753.4 | In Scope | SAP ECC Node B (was HANA)
10 | RCHSOLMAN72 | CtrlS → AWS | EC2 - Prod (SAP) | Hyderabad | r6a.2xlarge | 511.37 | 6136.44 | In Scope | SolMan (no longer HANA)
11 | Rainbow-NC-VCiso | CtrlS → AWS | EC2 - Prod | Hyderabad | m6a.2xlarge | 190.96 | 2291.52 | In Scope | vCISO Security
12 | Rainbow-NC-Syslog | CtrlS → AWS | EC2 - Prod | Hyderabad | c6a.2xlarge | 168.73 | 2024.76 | In Scope | Syslog
13 | RAINBOW80992 | CtrlS → AWS | EC2 - Prod | Hyderabad | m6a.2xlarge | 379.34 | 4552.08 | In Scope | IVF Clinical
14 | mobileapp | CtrlS → AWS | EC2 - Prod | Hyderabad | m6a.4xlarge | 276.68 | 3320.16 | In Scope | Mobile App
CtrlS NON-PRODUCTION (PDF Validated)
15 | RCHECCDEC | CtrlS → AWS | EC2 - Non-Prod (SAP) | Hyderabad | m6a.xlarge | 139.53 | 1674.36 | In Scope | SAP ECC QA/Dev
16 | RNBWHYDFDBK | CtrlS → AWS | EC2 - Non-Prod | Hyderabad | t3.medium | 24.41 | 292.92 | In Scope | Feedback
17 | RainbowC52431 | CtrlS → AWS | EC2 - Non-Prod | Hyderabad | t3.xlarge | 51.48 | 617.76 | In Scope | ICU Monitor
18 | SAP_PI_DEV | CtrlS → AWS | EC2 - Non-Prod (SAP) | Hyderabad | m6a.xlarge | 98.9 | 1186.8 | In Scope | SAP PI Dev
19 | sapgst | CtrlS → AWS | EC2 - Non-Prod (SAP) | Hyderabad | m6a.xlarge | 93.78 | 1125.36 | In Scope | SAP GST
20 | BIUAT-MIS | CtrlS → AWS | EC2 - Non-Prod | Hyderabad | t3.xlarge | 49.82 | 597.84 | In Scope | BI UAT
21 | Manage_Engine | CtrlS → AWS | EC2 - Non-Prod | Hyderabad | t3.2xlarge | 138.08 | 1656.96 | In Scope | ManageEngine
22 | Rainbow-HIS-UAT | CtrlS → AWS | EC2 - Non-Prod | Hyderabad | r6a.2xlarge | 276.36 | 3316.32 | In Scope | HIS UAT
23 | SAP-DevTesting | CtrlS → AWS | EC2 - Non-Prod (SAP) | Hyderabad | m6a.2xlarge | 141.15 | 1693.8 | In Scope | SAP ECC Dev (was HANA)
24 | SAP-QASTesting | CtrlS → AWS | EC2 - Non-Prod (SAP) | Hyderabad | r6a.4xlarge | 550.83 | 6609.96 | In Scope | SAP ECC QA (was HANA)
DR — MUMBAI (PDF Validated)
25 | RAINDC03 DR | CtrlS → AWS DR | EC2 - DR | Mumbai | m6i.xlarge | 226.67 | 2720.04 | In Scope | AD DC DR
26 | Rchbbserver DR | CtrlS → AWS DR | EC2 - DR | Mumbai | m6a.2xlarge | 1114.8 | 13377.6 | In Scope | Blood Bank DR
27 | RCHAEON DR | CtrlS → AWS DR | EC2 - DR | Mumbai | r6a.2xlarge | 1221.95 | 14663.4 | In Scope | Biometric DR
28 | Rainbow_MRD DR | CtrlS → AWS DR | EC2 - DR | Mumbai | c6a.8xlarge | 3319.81 | 39837.72 | In Scope | MRD DR
29 | SAP_PI_PRD DR | CtrlS → AWS DR | EC2 - DR (SAP) | Mumbai | m6a.2xlarge | 477.84 | 5734.08 | In Scope | SAP PI DR
30 | repsapGRP DR | CtrlS → AWS DR | EC2 - DR (SAP) | Mumbai | r6a.2xlarge | 780.14 | 9361.68 | In Scope | SAP ECC DR A
31 | repsapAPP DR | CtrlS → AWS DR | EC2 - DR (SAP) | Mumbai | r6a.2xlarge | 609.84 | 7318.08 | In Scope | SAP ECC DR B
32 | RCHSOLMAN72 DR | CtrlS → AWS DR | EC2 - DR (SAP) | Mumbai | r6a.xlarge | 320.76 | 3849.12 | In Scope | SolMan DR
33 | RAINBOW80992 DR | CtrlS → AWS DR | EC2 - DR | Mumbai | m6a.large | 119.46 | 1433.52 | In Scope | IVF DR
34 | mobileapp DR | CtrlS → AWS DR | EC2 - DR | Mumbai | m6a.2xlarge | 450.48 | 5405.76 | In Scope | Mobile DR
EXISTING AWS HMS (Phase 2)
35 | AAHISRPTSERV02 | Existing AWS | EC2 | Hyderabad | m6a.2xlarge | 104.32 | 1251.84 | Phase 2 | HMS Report 2
36 | AAINTFACESERV02 | Existing AWS | EC2 | Hyderabad | m6a.2xlarge | 99.76 | 1197.12 | Phase 2 | Interface 2
37 | AAHISAPPSERV02 | Existing AWS | EC2 | Hyderabad | m6a.2xlarge | 99.76 | 1197.12 | Phase 2 | HMS App 2
38 | AAHISAPPSERV03 | Existing AWS | EC2 | Hyderabad | m6a.2xlarge | 99.76 | 1197.12 | Phase 2 | HMS App 3
39 | MIRTHDBSERV01-DR | Existing AWS | EC2 | Hyderabad | m6a.large | 113.77 | 1365.24 | Phase 2 | Mirth DR
40 | AAINTFACESERV01 | Existing AWS | EC2 | Hyderabad | m6a.2xlarge | 99.76 | 1197.12 | Phase 2 | Interface 1
41 | AAHISAPPSERV01 | Existing AWS | EC2 | Hyderabad | m6a.2xlarge | 99.76 | 1197.12 | Phase 2 | HMS App 1
42 | AAHISRPTSERV01 | Existing AWS | EC2 | Hyderabad | m6a.2xlarge | 99.76 | 1197.12 | Phase 2 | HMS Report 1
43 | MIRTHDBSERV01-Prod | Existing AWS | EC2 | Hyderabad | m6a.2xlarge | 192.01 | 2304.12 | Phase 2 | Mirth Primary
44 | DEPLOYSERV01 | Existing AWS | EC2 | Hyderabad | t3.small | 10.13 | 121.56 | Phase 2 | Deploy
45 | Grafana | Existing AWS | EC2 | Hyderabad | c6a.large | 71.21 | 854.52 | Phase 2 | Monitoring
46 | newserver | Existing AWS | EC2 | Hyderabad | t3.xlarge | 77.18 | 926.16 | Phase 2 | Confirm
47 | New-server-replica | Existing AWS | EC2 | Hyderabad | t3.xlarge | 77.18 | 926.16 | Phase 2 | Confirm
48 | Redshift | Existing AWS | Managed | Hyderabad | 2x dc2.large | 459.9 | 5518.8 | Phase 2 | Analytics
49 | HMS S3 | Existing AWS | Storage | Hyderabad | S3 8TB | 657.89 | 7894.68 | Phase 2 | HMS storage
50 | RDS MySQL | Existing AWS | Managed | Hyderabad | db.t4g.small | 56.77 | 681.24 | Phase 2 | HMS DB
51 | HMS ELB | Existing AWS | Network | Hyderabad | ALB+NLB | 41.76 | 501.12 | Phase 2 | LBs
52 | Glue | Existing AWS | Managed | Hyderabad | 2 DPUs | 1.76 | 21.12 | Phase 2 | ETL
53 | VPC Transfer | Existing AWS | Network | Hyderabad | 4TB+16TB | 775.37 | 9304.44 | Phase 2 | Network
54 | GuardDuty | Existing AWS | Security | Hyderabad | Various | 224.4 | 2692.8 | Phase 2 | Threat
55 | CloudWatch | Existing AWS | Monitor | Hyderabad | 320m 122GB | 179.04 | 2148.48 | Phase 2 | Monitor
56 | Backup | Existing AWS | Backup | Hyderabad | 3.5TB | 235.38 | 2824.56 | Phase 2 | Backup
57 | HMS DRS | Existing AWS | DR | Mumbai | 10 servers | 951.78 | 11421.36 | Phase 2 | DRS
58 | Redshift DR | Existing AWS | DR | Mumbai | Backup | 25 | 300 | Phase 2 | Redshift DR
59 | S3 CRR | Existing AWS | DR | Mumbai | 8TB | 657.89 | 7894.68 | Phase 2 | S3 DR
60 | RDS CRR | Existing AWS | DR | Mumbai | db.t4g.small | 81.59 | 979.08 | Phase 2 | RDS DR
61 | ELB DR | Existing AWS | DR | Mumbai | ALB+NLB | 41.76 | 501.12 | Phase 2 | DR LBs
62 | GuardDuty DR | Existing AWS | DR | Mumbai | Various | 224.4 | 2692.8 | Phase 2 | DR sec
63 | CloudWatch DR | Existing AWS | DR | Mumbai | 100m | 64.48 | 773.76 | Phase 2 | DR mon
64 | Backup CRR | Existing AWS | DR | Mumbai | 3.5TB | 312.7 | 3752.4 | Phase 2 | DR backup
SUPPORTING SERVICES (PDF Updated)
65 | DT Intra+Inbound | Supporting | Network | Hyderabad | 3.5 TB | 69 | 828 | In Scope | PDF combined
66 | DT Egress | Supporting | Network | Hyderabad | 2.5 TB | 234.25 | 2811 | In Scope | Internet
67 | VPC+NAT | Supporting | Network | Hyderabad | NAT+VPN | 271.14 | 3253.68 | In Scope | HA NAT
68 | Inspector | Supporting | Security | Hyderabad | 24 EC2 | 36.24 | 434.88 | In Scope | PDF calc
69 | GuardDuty | Supporting | Security | Hyderabad | Flow+EBS | 244.6 | 2935.2 | In Scope | Threat
70 | Config | Supporting | Compliance | Hyderabad | Continuous | 18.5 | 222 | In Scope | Audit
71 | Security Hub | Supporting | Security | Hyderabad | CSPM | 85 | 1020 | In Scope | Dashboard
72 | CloudTrail | Supporting | Compliance | Hyderabad | Mgmt+data | 0.2 | 2.4 | In Scope | Logging
73 | WAF | Supporting | Security | Hyderabad | 1 ACL+5 | 12.2 | 146.4 | In Scope | Web
74 | CloudWatch | Supporting | Monitor | Hyderabad | 150m 40GB | 84.28 | 1011.36 | In Scope | Monitor
75 | Backup | Supporting | Backup | Hyderabad | 5TB | 550 | 6600 | In Scope | 365-day retention
76 | ELB 3xALB | Supporting | Network | Hyderabad | 3 ALBs | 74.24 | 890.88 | In Scope | Public
77 | S3 Standard | Supporting | Storage | Hyderabad | 2 TB | 52.74 | 632.88 | In Scope | Logs
78 | S3 IT | Supporting | Storage | Hyderabad | 10TB MRD | 90 | 1080 | In Scope | Archival
79 | Sys Manager | Supporting | Mgmt | Hyderabad | Patch | 0 | 0 | In Scope | Free
80 | KMS | Supporting | Security | Hyderabad | 3 CMKs | 3.3 | 39.6 | In Scope | PDF calc
81 | Route 53 | Supporting | Network | Global | Failover | 6.1 | 73.2 | In Scope | PDF calc
82 | DRS | Supporting | DR | Mumbai | 7 servers | 1191.28 | 14295.36 | In Scope | PDF calc
83 | Inter-Region | Supporting | Network | HYD↔MUM | 3TB | 61.5 | 738 | In Scope | Cross-region
84 | VPC+NAT DR | Supporting | Network | Mumbai | NAT+VPN | 271.14 | 3253.68 | In Scope | PDF calc
85 | Inspector DR | Supporting | Security | Mumbai | DR scan | 70 | 840 | In Scope | DR
86 | Backup DR | Supporting | Backup | Mumbai | CRR | 380 | 4560 | In Scope | 365-day CRR
87 | CloudWatch DR | Supporting | Monitor | Mumbai | DR | 69.11 | 829.32 | In Scope | PDF calc
88 | ELB DR | Supporting | Network | Mumbai | 3 ALBs | 74.24 | 890.88 | In Scope | PDF calc
89 | GuardDuty DR | Supporting | Security | Mumbai | DR | 98.3 | 1179.6 | In Scope | DR
MARKETPLACE (PALO ALTO 365-DAY + MONGODB)
90 | PA EC2 HYD | Marketplace | Firewall | Hyderabad | 2x c6i.xlarge | 139 | 1668 | In Scope | CSP 3yr
91 | PA EBS HYD | Marketplace | Firewall | Hyderabad | 2x 100GB gp3 | 18.24 | 218.88 | In Scope | OS+logs
92 | GWLB HYD | Marketplace | Firewall | Hyderabad | GWLB | 20 | 240 | In Scope | Routing
93 | PA 365-day HYD | Marketplace | Firewall | Hyderabad | PAYG 365-day | 724 | 8688 | In Scope | 71% off
94 | PA EC2 DR | Marketplace | Firewall | Mumbai | 2x c6i.xlarge | 80 | 960 | In Scope | Standby
95 | PA EBS DR | Marketplace | Firewall | Mumbai | 2x 100GB gp3 | 18.24 | 218.88 | In Scope | DR EBS
96 | GWLB DR | Marketplace | Firewall | Mumbai | GWLB DR | 20 | 240 | In Scope | Standby
97 | PA 365-day DR | Marketplace | Firewall | Mumbai | PAYG 365-day | 724 | 8688 | In Scope | DR pair
98 | MongoDB 1 | Marketplace | Database | Hyderabad | M40 16GB | 800 | 9600 | In Scope | Primary
99 | MongoDB 2 | Marketplace | Database | Hyderabad | M50 32GB | 1200 | 14400 | In Scope | Secondary
100 | MongoDB SAP | Marketplace | Database | Hyderabad | M30 8GB | 450 | 5400 | In Scope | SAP
101 | MongoDB DR | Marketplace | Database | Mumbai | Cross-region | 980 | 11760 | In Scope | 30-40%
102 | CRM | Marketplace | SaaS | Hyderabad | TBC | 0 | 0 | Pending | ⚠️ Pending
103 | HMS BOQ | Marketplace | SaaS | Hyderabad | TBC | 0 | 0 | Pending | Done
REMOVED — PACS & AD out of scope
CONSOLIDATED TOTALS (PDF-Validated)
| CtrlS Production |  |  |  |  | 10962.73 | 131552.76
| CtrlS Non-Prod |  |  |  |  | 1387.59 | 16651.08
| DR Mumbai |  |  |  |  | 8281.29 | 99375.48
| Existing AWS HMS |  |  |  |  | 6209.14 | 74509.68
| Supporting Services |  |  |  |  | 3948.48 | 47381.76
| Marketplace |  |  |  |  | 5173.08 | 62076.96
| GRAND TOTAL (Confirmed) |  |  |  |  | 35962.31 | 431547.72
| TCO | https://calculator.aws/#/estimate?id=577f59faba382953de9dad436fb4133589ba6d61
| MRR | 36181.08
| ARR | 434175.58

## Consolidated Summary
Rainbow Hospitals – Final Consolidated TCO (30-Apr-2026 — v1.3, PDF-validated)
Primary: Hyderabad ¦ DR: Mumbai Active-Passive ¦ Phase 2: HMS to HYD
| Category | Monthly (USD) | Annual (USD) | Notes
| Primary - Production Servers (CSP 3yr) | 10962.73 | 131552.76 | CSP 3yr No Upfront ~50% discount.
| Primary - Non-Prod Servers (OD best) | 1387.59 | 16651.08 | Cheaper of 75% util or 8hr/day.
| DR - Mumbai (Active-Passive) | 8281.29 | 99375.48 | 10 critical servers pilot-light.
| Supporting Services (HYD + Mumbai) | 3948.48 | 47381.76 | Inspector, Backup, Config, WAF, DRS.
| Marketplace Offerings (Palo Alto + MongoDB) | 5173.08 | 62076.96 | Palo Alto PAYG 365-day + MongoDB Atlas. No BYOL.
| Existing AWS HMS (Phase 2) | 6209.14 | 74509.68 | Moving Mumbai → HYD + DR Mumbai.
| GRAND TOTAL (Complete Rainbow AWS Landscape) | 35962.31 | 431547.72 | Phase 1 + Phase 2 + DR + Marketplace + AD/PACS
|  | 30789.23 | 369470.76 | Excluding Marketplace offerings | 369540.94 | -431547.72 | 0
|  | 29753.17 | 357038.04 | Excluding Phase 2 (Existing AWS HMS)
🔴 HYD Availability Corrections Applied
CtrlS Primary: RNBWHYDFDBK, RainbowC52431, BIUAT-MIS, Manage_Engine
→ T3a replaced with T3 (Windows) or T3 (Linux/Intel - cheaper)
Existing HMS: DEPLOYSERV01, newserver-26-08-2025, New-server-replica
→ T3a replaced with T3 (Windows) or T3 (Linux)
Net impact: ~+$45/mo (T3 replacements) - ~$25/mo (T3 savings on Linux) = minimal
📊 Comparison with Previous TCO
TCO 24-Apr (PDF): $30,794.86/mo ¦ $369,540.94/yr (AWS Pricing Calculator)
TCO 25-Apr: See Grand Total above (includes AD/PACS + Marketplace)
📋 Next Steps
1. Share Active-Active quote (Chari requested) — see dedicated sheet
2. Follow up with Chari for CPU/RAM utilisation data
3. Intel compatibility for HIS — T3 successfully used for Ubuntu UAT
4. Palo Alto: 365-day PAYG confirmed — no BYOL. Annual commitment with AWS.
5. Confirm MongoDB Atlas single-region vs multi-region DR with Chari
6. Confirm 2 unknown Windows servers (newserver-26-08-2025)
7. Phase 2 timeline: existing AWS Mumbai → Hyderabad
8. SAP HANA r6i.2xlarge certification risk discussion with Chari
10. AD & PACS: Confirm PACS server specs from customer to finalize sizing
11. AD & PACS: Confirm PACS imaging storage volume for FSx sizing

## Primary TCO - Hyderabad
Primary Region: Hyderabad (ap-south-2) — ControlS Migration ¦ HYD Availability Validated
S.No | Server Name | Scope | SAP? | Group | OS | Processor | Instance | vCPU | RAM (GB) | Pricing | EBS (GB) | EBS Type | Disk Util % | EC2 $/mo | EBS $/mo | Total $/mo | Sizing Justification
1 | RAINDC03 | In Scope | No | Production | Windows Server 2019 | Intel | m6i.xlarge | 4 | 16 | CSP 3yr No Upfront | 200 | gp3 | No data provided | 208.43 | 18.24 | 226.67 | AD Primary DC. Intel M6i (4 vCPU / 16 GB) matches source allocation.
2 | RAINDC02 | In Scope | No | Production | Windows Server 2019 | Intel | m6i.xlarge | 4 | 16 | CSP 3yr No Upfront | 200 | gp3 | No data provided | 208.43 | 18.24 | 226.67 | AD Secondary DC. Placed in different AZ for high availability.
3 | RCHECCDEC | In Scope | YES | Non-Prod | Windows 2012 R2→2019 | AMD | m6a.xlarge | 4 | 16 | OD 8hr/day | 2250 | gp3 | Disk: 85.71% | 139.53 | 0 | 139.53 | SAP ECC Quality/Dev. AMD M6a certified for SAP NetWeaver. EBS increased to 2250 GB for disk headroom.
4 | HISPRODDB01_new | OUT OF SCOPE | No | Legacy | Windows 2012 R2 | - | - | - | - | - | - | - | Disk: 88.67% | - | - | - | Legacy HIS DB — confirmed for decommission. Not migrated to AWS.
5 | WIN-AKB5JTJTA8S | OUT OF SCOPE | No | Legacy | Windows 2012 R2 | - | - | - | - | - | - | - | No data provided | - | - | - | Legacy HIS SQL Server — not migrated. Decommission on-prem.
6 | HISPRODAPP02 | OUT OF SCOPE | No | Legacy | Windows 2012 R2 | - | - | - | - | - | - | - | Disk: 99.82% | - | - | - | Legacy HIS App Server — not migrated. Disk at critical capacity.
7 | Rchbbserver (Blood Bank) | In Scope | No | Production | Windows Server 2019 | AMD | m6a.4xlarge | 16 | 64 | CSP 3yr No Upfront | 700 | gp3 | No data provided | 2101.93 | 63.84 | 2165.77 | Blood Bank + SQL Server Standard. AMD M6a.4xlarge (16 vCPU / 64 GB). Windows SQL required. io2 EBS for ACID compliance.
8 | Rainbow_MRD_64703_NEW | In Scope | No | Production | Ubuntu Pro 22.04 | AMD | c6a.8xlarge | 32 | 64 | CSP 3yr No Upfront | 21500 | gp3 | Disk: 85.13% | 310.11 | 1960.8 | 2270.91 | MRD OCR compute-intensive. AMD C6a.8xlarge (32 vCPU / 64 GB). Recommend S3 Intelligent-Tiering for cold archive data.
9 | RNBWHYDFDBK | In Scope | No | Non-Prod | Windows Server 2022 | Intel | t3.medium | 2 | 4 | OD 8hr/day | 300 | gp3 | No data provided | 24.41 | 0 | 24.41 | Legacy Feedback application. Non-production burstable workload.
10 | RainbowC52431 | In Scope | No | Non-Prod | Ubuntu Pro 22.04 | Intel | t3.xlarge | 4 | 16 | OD 8hr/day | 205 | gp3 | No data provided | 28.68 | 22.8 | 51.48 | ICU monitoring. Non-production burstable. Ubuntu 16.04 EOL — upgrade to 22.04 during migration.
11 | RCHAEON (Biometric) | In Scope | No | Production | Windows Server 2019 | AMD | r6a.4xlarge | 16 | 128 | CSP 3yr No Upfront | 1100 | gp3 | No data provided | 2157.76 | 100.32 | 2258.08 | Biometric + SQL Server Standard. AMD R6a.4xlarge (16 vCPU / 128 GB). io2 EBS for transactional consistency.
12 | RainbowRPA | In Scope | No | Production | Windows Server 2019 | AMD | m6a.2xlarge | 8 | 32 | CSP 3yr No Upfront | 350 | gp3 | No data provided | 345.6 | 36.48 | 382.08 | RPA and Reporting server. AMD M6a.2xlarge (8 vCPU / 32 GB) general-purpose.
13 | SAP_PI_PRD_New | In Scope | YES | Production | Windows Server 2019 | AMD | m6a.4xlarge | 16 | 64 | CSP 3yr No Upfront | 1400 | gp3 | Disk: 90.09% | 702.43 | 127.68 | 830.11 | SAP PI/PO Production. AMD M6a.4xlarge certified for SAP NetWeaver. EBS 1400 GB (headroom from 90% disk util).
14 | SAP_PI_DEV_New | In Scope | YES | Non-Prod | Windows Server 2019 | AMD | m6a.xlarge | 4 | 16 | OD 8hr/day | 900 | gp3 | Disk: 81.59% | 16.82 | 82.08 | 98.9 | SAP PI/PO Development. AMD M6a certified for SAP NetWeaver non-production.
15 | repsapGRP (SAPPRDclusA) | In Scope | YES | Production | Windows Server 2022 | AMD | r6a.2xlarge | 8 | 64 | CSP 3yr No Upfront | 2400 | gp3 | No data provided | 379.13 | 218.88 | 598.01 | SAP ECC Production (was HANA — now out of scope). AMD R6a.2xlarge (8/64). EBS io2→gp3. SAP NetWeaver certified on AMD.
16 | repsapAPP (SAPPRDclusB) | In Scope | YES | Production | Windows Server 2022 | AMD | r6a.2xlarge | 8 | 64 | CSP 3yr No Upfront | 1100 | gp3 | No data provided | 379.13 | 100.32 | 479.45 | SAP ECC Production Node B. AMD R6a.2xlarge (8/64). EBS io2→gp3. SAP NetWeaver certified on AMD.
17 | RCHSOLMAN72 | In Scope | YES | Production | Windows Server 2019 | AMD | r6a.2xlarge | 8 | 64 | CSP 3yr No Upfront | 1450 | gp3 | Disk: 86.54% | 377.03 | 132.24 | 509.27 | SAP Solution Manager 7.2. AMD R6a.2xlarge (8/64). HANA no longer required — SolMan on AnyDB. SAP NetWeaver certified on AMD.
18 | sapgst | In Scope | YES | Non-Prod | Windows 2012→2019 | AMD | m6a.xlarge | 4 | 16 | OD 8hr/day | 730 | gp3 | Disk: 84.76% | 16.26 | 77.52 | 93.78 | SAP GST Development Sandbox. AMD M6a certified for SAP NetWeaver. Windows Server 2012 EOL — upgrade during migration.
19 | BIUAT-MIS | In Scope | No | Non-Prod | Ubuntu Pro 22.04 | Intel | t3.xlarge | 4 | 16 | OD 8hr/day | 150 | gp3 | Disk: 80.25% | 33.4 | 16.42 | 49.82 | BI/MIS UAT environment. T3 Intel burstable for non-production workload.
20 | Manage_Engine | In Scope | No | Non-Prod | Windows Server 2019 | Intel | t3.2xlarge | 8 | 32 | OD 8hr/day | 500 | gp3 | No data provided | 92.48 | 45.6 | 138.08 | ManageEngine IT Management. Non-production burstable. Evaluate replacement with CloudWatch post-migration.
21 | Rainbow-NC-VCiso | In Scope | No | Production | Ubuntu Pro 22.04 | AMD | m6a.2xlarge | 8 | 32 | CSP 3yr No Upfront | 1127 | gp3 | No data provided | 81.52 | 109.44 | 190.96 | Nopal Cyber Security vCISO platform. AMD M6a.2xlarge (8 vCPU / 32 GB). Production security workload.
22 | Rainbow-NC-Syslog | In Scope | No | Production | Ubuntu Pro 22.04 | AMD | c6a.2xlarge | 8 | 16 | CSP 3yr No Upfront | 1000 | gp3 | No data provided | 77.53 | 91.2 | 168.73 | Syslog Server. T3 Intel for consistent log ingestion performance.
23 | Rainbow-HIS-UAT | In Scope | No | Non-Prod | Ubuntu Pro 22.04 | AMD | r6a.2xlarge | 8 | 64 | OD 8hr/day | 1639 | gp3 | No data provided | 121.32 | 155.04 | 276.36 | HIS UAT for Arcus Air (new HIS). R6a AMD provides 64 GB RAM to match source 48 GB allocation with headroom.
24 | RAINBOW80992 | In Scope | No | Production | Windows Server 2022 | AMD | m6a.2xlarge | 8 | 32 | CSP 3yr No Upfront | 320 | gp3 | No data provided | 347.42 | 31.92 | 379.34 | IVF Clinical Application. AMD M6a.2xlarge (8 vCPU / 32 GB). Production-critical.
25 | SAP-DevTesting | In Scope | YES | Non-Prod | Windows Server 2022 | AMD | r6a.xlarge | 4 | 32 | OD 8hr/day | 1100 | gp3 | Disk: 80.74% | 79.57 | 33.11 | 112.68 | SAP ECC Development (was HANA Dev). AMD M6a.2xlarge (8/32). Downsized — ECC dev doesn't need 64 GB. Non-production OD 8hr/day.
26 | SAP-QASTesting | In Scope | YES | Non-Prod | Windows Server 2022 | AMD | r6a.4xlarge | 16 | 128 | OD 8hr/day | 2800 | gp3 | No data provided | 318.28 | 84.27 | 402.55 | SAP ECC QA/Staging (was HANA QAS). AMD R6a.4xlarge (16/128). EBS io2→gp3. Non-production OD 8hr/day.
27 | mobileapp | In Scope | No | Production | Ubuntu Pro 24.04 | AMD | m6a.4xlarge | 16 | 64 | CSP 3yr No Upfront | 1100 | gp3 | Disk: 79.56% | 176.36 | 100.32 | 276.68 | Mobile App + Rainbow Shield. AMD M6a.4xlarge (16 vCPU / 64 GB). Evaluate Graviton post-migration.
Production Servers Total (CSP 3yr) | [15 empty] | 10962.73
Non-Prod Servers Total (OD best option) | [15 empty] | 1387.59
TOTAL — Primary Region (Hyderabad) | [15 empty] | 12350.32

## DR TCO - Mumbai
DR Region: Mumbai (ap-south-1) — Active-Passive Multi-Region DR
S.No | Server Name | SAP? | DR Mode | OS | Processor | Instance | vCPU | RAM (GB) | Pricing | EBS (GB) | EBS Type | EC2 $/mo | EBS $/mo | Total $/mo | DR Justification
1 | RAINDC03 (DR) | No | Active-Passive | Windows Server 2019 | Intel | m6i.xlarge | 4 | 16 | CSP 3yr No Upfront | 200 | gp3 | 208.43 | 18.24 | 226.67 | AD Domain Controller DR. Pilot-light (m6i.large) for authentication services. AD multi-site replication.
2 | Rchbbserver (DR) | No | Active-Passive | Windows Server 2019 | AMD | m6a.2xlarge | 8 | 32 | CSP 3yr No Upfront | 700 | gp3 | 1050.96 | 63.84 | 1114.8 | Blood Bank DR. AMD M6a.2xlarge pilot-light (8 vCPU vs 16 vCPU prod). SQL Always-On async replication.
3 | RCHAEON (DR) | No | Active-Passive | Windows Server 2019 | AMD | r6a.2xlarge | 8 | 64 | CSP 3yr No Upfront | 1100 | gp3 | 1077.85 | 100.32 | 1178.17 | Biometric DR. AMD R6a.2xlarge pilot-light (64 GB vs 128 GB prod). SQL Always-On replication.
4 | Rainbow_MRD (DR) | No | Active-Passive | Ubuntu Pro 22.04 | AMD | c6a.8xlarge | 32 | 64 | CSP 3yr No Upfront | 21500 | gp3 | 1359.01 | 1960.8 | 3319.81 | MRD DR. AMD C6a.8xlarge full-size replica for 21 TB data replication.
5 | SAP_PI_PRD (DR) | YES | Active-Passive | Windows Server 2019 | AMD | m6a.2xlarge | 8 | 32 | CSP 3yr No Upfront | 1400 | gp3 | 350.16 | 127.68 | 477.84 | SAP PI/PO DR. AMD M6a.2xlarge pilot-light (8 vCPU vs 16 vCPU prod). Queue replication.
6 | repsapGRP (DR) | YES | Active-Passive | Windows Server 2022 | AMD | r6a.2xlarge | 8 | 64 | CSP 3yr No Upfront | 2400 | gp3 | 377.05 | 218.88 | 595.93 | SAP ECC DR Node A. AMD R6a.2xlarge. EBS io2→gp3. Async replication to Mumbai.
7 | repsapAPP (DR) | YES | Active-Passive | Windows Server 2022 | AMD | r6a.2xlarge | 8 | 64 | CSP 3yr No Upfront | 1100 | gp3 | 377.05 | 100.32 | 477.37 | SAP ECC DR Node B. AMD R6a.2xlarge. EBS io2→gp3. Symmetric to Node A.
8 | RCHSOLMAN72 (DR) | YES | Active-Passive | Windows Server 2019 | AMD | r6a.xlarge | 4 | 32 | CSP 3yr No Upfront | 1450 | gp3 | 188.52 | 132.24 | 320.76 | SAP SolMan DR. AMD R6a.xlarge pilot-light (32 GB vs 64 GB prod). Standby.
9 | RAINBOW80992 (DR) | No | Active-Passive | Windows Server 2022 | AMD | m6a.large | 2 | 8 | CSP 3yr No Upfront | 350 | gp3 | 87.54 | 31.92 | 119.46 | IVF Clinical DR. AMD M6a.large pilot-light (2 vCPU vs 8 vCPU prod). Scale-up on failover.
10 | mobileapp (DR) | No | Active-Passive | Ubuntu Pro 24.04 | AMD | m6a.2xlarge | 8 | 32 | CSP 3yr No Upfront | 1100 | gp3 | 350.16 | 100.32 | 450.48 | Mobile App DR. AMD M6a.2xlarge pilot-light. Ubuntu matching primary OS.
ℹ️ Mumbai has full instance catalogue. All instances used here are available. 10 critical servers in pilot-light mode.
TOTAL DR — Mumbai (Active-Passive) | [13 empty] | 8281.29

## SuppServices4ExistingHIS
Supporting Services — Hyderabad (Primary) + Mumbai (DR) ¦ Availability Validated
S.No | Service | Region | Configuration | HYD/Mumbai Avail | Monthly $ | Notes
1 | Data Transfer (Intra + Inbound) | Hyderabad | 1.5 TB intra-region/mo | ✅ Available | 69 | Within HYD region.
2 | Data Transfer - Egress | Hyderabad | 2.5 TB out/mo to internet | ✅ Available | 234.25 | Internet-bound traffic.
3 | VPC + NAT Gateway | Hyderabad | VPN + NAT Gateway (PDF-aligned) | ✅ Available | 329.83 | HA NAT. VPN to customer DC.
4 | AWS Inspector | Hyderabad | Vulnerability scanning 24 EC2 instances | ✅ Available | 36.24 | Replaces EDR. Native AWS.
5 | GuardDuty | Hyderabad | Flow logs + EBS scan + CloudTrail | ✅ Available | 244.6 | Threat detection.
6 | AWS Config | Hyderabad | Continuous config monitoring | ✅ Available | 18.5 | Compliance + audit.
7 | AWS Security Hub | Hyderabad | CSPM + findings aggregation | ✅ Available | 85.01 | Central security dashboard.
8 | CloudTrail | Hyderabad | Management + data events | ✅ Available | 0.2 | Audit logging.
9 | WAF | Hyderabad | 1 Web ACL + 5 rules | ✅ Available | 12.2 | IVF + Mobile App + HIS UAT.
10 | CloudWatch | Hyderabad | 150 metrics + 40GB logs | ✅ Available | 84.28 | Monitoring.
11 | AWS Backup | Hyderabad | 5 TB, 365-day retention | ✅ Available | 391.78 | Replaces CommVault.
12 | ELB (3x ALB) | Hyderabad | 3 Application Load Balancers | ✅ Available | 74.24 | Public-facing apps.
13 | S3 Standard (2 TB) | Hyderabad | Logs, backups, archival | ✅ Available | 52.74 | Object storage.
14 | S3 Intelligent Tiering | Hyderabad | 10 TB MRD cold data | ✅ Available | 0 | MRD archival (Phase 2).
15 | Systems Manager | Hyderabad | Patch Manager + Run Command | ✅ Available | 0 | Free tier.
16 | KMS | Hyderabad | 5 CMKs + 200K requests | ✅ Available | 3.3 | Encryption.
17 | Route 53 | Global | Hosted zones + failover health checks | ✅ Global | 6.1 | DNS failover.
18 | AWS DRS (Cross-Region) | Mumbai | 10 critical servers replication | ✅ Available | 1191.28 | DRS from HYD.
19 | Data Transfer (Inter-Region) | HYD↔Mumbai | 2 TB/mo cross-region replication (PDF-aligned) | ✅ Available | 176.13 | ~$0.020/GB.
20 | VPC + NAT Gateway (DR) | Mumbai | VPN + NAT Gateway DR region (PDF-aligned) | ✅ Available | 329.83 | DR networking.
21 | AWS Inspector (DR) | Mumbai | DR instance scanning | ✅ Available | 15.1 | Native security.
22 | AWS Backup (DR) | Mumbai | Cross-region backup copy | ✅ Available | 295.62 | DR retention.
23 | S3 (DR Cross-Region Replica) | Mumbai | 2 TB CRR storage | ✅ Available | 56.6 | S3 Standard 2TB CRR replica from HYD (PDF-validated 30-Apr-2026)
24 | CloudWatch (DR) | Mumbai | DR monitoring | ✅ Available | 69.11 | DR observability.
25 | ELB (DR) | Mumbai | 1 ALB for DR failover | ✅ Available | 74.24 | DR ALB.
26 | GuardDuty (DR) | Mumbai | DR threat detection | ✅ Available | 98.3 | DR security.
TOTAL Supporting Services |  |  |  |  | 3948.48

## Supporting Services
Supporting Services — Hyderabad (Primary) + Mumbai (DR) ¦ Availability Validated
S.No | Service | Region | Configuration | HYD/Mumbai Avail | Monthly $ | Notes
1 | Data Transfer (Intra + Inbound) | Hyderabad | 1.5 TB intra-region/mo | ✅ Available | 69 | Within HYD region.
2 | Data Transfer - Egress | Hyderabad | 2.5 TB out/mo to internet | ✅ Available | 234.25 | Internet-bound traffic.
3 | VPC + NAT Gateway | Hyderabad | NAT GW in 2 AZs + S2S VPN | ✅ Available | 271.14 | HA NAT. VPN to customer DC.
4 | AWS Inspector | Hyderabad | Vulnerability scanning 24 EC2 instances | ✅ Available | 36.24 | Replaces EDR. Native AWS.
5 | GuardDuty | Hyderabad | Flow logs + EBS scan + CloudTrail | ✅ Available | 244.6 | Threat detection.
6 | AWS Config | Hyderabad | Continuous config monitoring | ✅ Available | 18.5 | Compliance + audit.
7 | AWS Security Hub | Hyderabad | CSPM + findings aggregation | ✅ Available | 85 | Central security dashboard.
8 | CloudTrail | Hyderabad | Management + data events | ✅ Available | 0.2 | Audit logging.
9 | WAF | Hyderabad | 1 Web ACL + 5 rules | ✅ Available | 12.2 | IVF + Mobile App + HIS UAT.
10 | CloudWatch | Hyderabad | 150 metrics + 40GB logs | ✅ Available | 84.28 | Monitoring.
11 | AWS Backup | Hyderabad | 5 TB primary, 365-day warm retention (customer requirement) | ✅ Available | 550 | 365-day retention per customer. Est: 5TB primary + 365 days incremental. ⚠️ Validate in AWS Calculator.
12 | ELB (3x ALB) | Hyderabad | 3 Application Load Balancers | ✅ Available | 74.24 | Public-facing apps.
13 | S3 Standard (2 TB) | Hyderabad | Logs, backups, archival | ✅ Available | 52.74 | Object storage.
14 | S3 Intelligent Tiering | Hyderabad | 10 TB MRD cold data | ✅ Available | 90 | MRD archival (Phase 2).
15 | Systems Manager | Hyderabad | Patch Manager + Run Command | ✅ Available | 0 | Free tier.
16 | KMS | Hyderabad | 5 CMKs + 200K requests | ✅ Available | 3.3 | Encryption.
17 | Route 53 | Global | Hosted zones + failover health checks | ✅ Global | 6.1 | DNS failover.
18 | AWS DRS (Cross-Region) | Mumbai | 10 critical servers replication | ✅ Available | 1191.28 | DRS from HYD.
19 | Data Transfer (Inter-Region) | HYD↔Mumbai | 3 TB/mo cross-region replication | ✅ Available | 61.5 | ~$0.020/GB.
20 | VPC + NAT Gateway (DR) | Mumbai | NAT GW + VPN DR region | ✅ Available | 271.14 | DR networking.
21 | AWS Inspector (DR) | Mumbai | DR instance scanning | ✅ Available | 70 | Native security.
22 | AWS Backup (DR) | Mumbai | Cross-region backup copy, 365-day retention | ✅ Available | 380 | DR cross-region copy 365-day. ⚠️ Validate in AWS Calculator.
23 | CloudWatch (DR) | Mumbai | DR monitoring | ✅ Available | 69.11 | DR observability.
24 | ELB (DR) | Mumbai | 1 ALB for DR failover | ✅ Available | 74.24 | DR ALB.
25 | GuardDuty (DR) | Mumbai | DR threat detection | ✅ Available | 98.3 | DR security.
TOTAL Supporting Services |  |  |  |  | 4047.36

## Marketplace Offerings
AWS Marketplace Offerings — Palo Alto + MongoDB (HYD + Mumbai Validated)
S.No | Product | Region | Configuration | Availability | Monthly $ | Notes
1 | Palo Alto VM-Series (EC2) | Hyderabad | 2x c6i.xlarge HA pair | ✅ Available | 128.86 | VM-Series EC2 compute. 2x c6i.xlarge HA pair. CSP 3yr pricing.
2 | Palo Alto VM-Series (EBS) | Hyderabad | 2x 100 GB gp3 | ✅ Available | 18.24 | OS + logs storage.
3 | Gateway Load Balancer | Hyderabad | GWLB for Palo Alto HA | ✅ Available | 24.68 | Traffic routing.
4 | Palo Alto PAYG 365-day License | Hyderabad | 2x c6i.xlarge — PAYG 365-day (71% savings) | ✅ Marketplace | 724 | PAYG $1.71/hr → 365-day: $0.4959/hr × 730hr = $362/mo × 2 instances. Includes Adv Threat Prevention, URL Filtering, WildFire, DNS Security, GlobalProtect + 24x7 Premium Support. Source: aws.amazon.com/marketplace/pp/prodview-3xtziatyes54i
5 | Palo Alto DR (EC2) | Mumbai | 2x c6i.xlarge passive standby | ✅ Available | 80.3 | DR pair. Instances stopped until failover. EC2 compute only.
6 | Palo Alto DR (EBS) | Mumbai | 2x 100 GB gp3 | ✅ Available | 18.24 | DR EBS (provisioned).
7 | Gateway Load Balancer (DR) | Mumbai | GWLB DR | ✅ Available | 24.68 | Standby GWLB.
8 | Palo Alto PAYG 365-day (DR) | Mumbai | 2x c6i.xlarge — PAYG 365-day (DR pair) | ✅ Marketplace | 724 | DR pair: Same 365-day rate. License commits to annual contract regardless of instance state. Same security subs included.
9 | MongoDB Atlas HMIS Cluster 1 | Hyderabad (Atlas) | M40 - 16 GB / 750 GB | ✅ Since Mar 2025 | 800.02 | Primary HMS MongoDB cluster. Marketplace.
10 | MongoDB Atlas HMIS Cluster 2 | Hyderabad (Atlas) | M50 - 32 GB / 1,596 GB | ✅ Since Mar 2025 | 1200.02 | Secondary HMS. Marketplace.
11 | MongoDB Atlas App/SAP Cluster | Hyderabad (Atlas) | M30 - 8 GB / 200 GB | ✅ Since Mar 2025 | 450.02 | SAP-Atlas dependency.
12 | MongoDB Atlas Multi-Region DR | Mumbai (Atlas) | Cross-region replica premium | ✅ Available | 980.02 | 30-40% premium. Auto failover.
13 | Latespot CRM (placeholder) | Hyderabad | Marketplace Private Offer TBC | Pending | 0 | Vendor details pending Chari.
14 | HMS Vendor BOQ (placeholder) | Hyderabad | IQVIA/Care Expert/MyHealthcare | Pending | 0 | Pending Srini/Chari decision.
TOTAL Marketplace Offerings |  |  |  |  | 5173.08
🛒 Marketplace Availability Verification (24-Apr-2026)
• Palo Alto VM-Series: ✅ Available globally via AWS Marketplace (HYD + Mumbai)
• MongoDB Atlas: ✅ Hyderabad since March 2025, Mumbai long-standing
• Both counts toward MAP/PPA qualification via AWS Marketplace spend
⚠️ Action items:
1. Palo Alto: 365-day PAYG contract selected — no BYOL. Confirm annual commitment with AWS.
2. Confirm MongoDB single-region vs multi-region DR with Chari
3. Latespot CRM details pending Chari
4. HMS Vendor BOQ pending Srini/Chari decision
https://www.mongodb.com/products/platform/atlas-cloud-providers/aws/pricing
https://www.mongodb.com/docs/atlas/reference/amazon-aws/#std-label-amazon-aws
https://aws.amazon.com/marketplace/pp/prodview-3xtziatyes54i?sr=0-2&ref_=beagle&applicationId=AWSMPContessa
Requirements from Customer - 24th april 2026 (Minfy send email)
| PACS Infra details with Active Directory details |  | SAP Rise - Internal Check (Infra - Gopal, Functional - AWS)
CRM - SaaS details
HMS Vendor BOQ post discussion with vendor
Palo Alto License
HMS ARM Based architecture
Static page hosting with S3 + Cloudfront
CPU / RAM Utilization
Application Depedency (Server Depedent)
https://www.mongodb.com/pricing/calculator/estimate/69eca2abcf761e821c9acfed/cluster-configuration/69eca36bcf761e821c9acff7?name=Cluster+4&isAdvancedConfigExpanded=false&isBackupNetworkExpanded=false&isPrimaryConfigExpanded=true&region=AP_SOUTH_1&diskSizeGb=100

## HIS BOM - KareXpert
KareXpert — AWS BOM Detail ¦ 2,500 Beds ¦ Primary: Hyderabad (EKS/Kubernetes)
Containerised microservices on EKS (Kubernetes). 24 Graviton worker nodes. All Linux — available in ap-south-2.
# | Component | Instance/Config | Qty | vCPU | RAM (GB) | EC2 OD $/mo ea | EC2 CSP 3yr ea | Total $/mo | Notes
1 | EKS Cluster Control Plane | EKS Standard | 1 | - | - | 73 | 73 | 73 | Managed K8s control plane. $0.10/hr = $73/mo fixed.
2 | EKS Workers — Core Apps | r6g.xlarge | 18 | 4 | 32 | 134.32 | 58.18 | 1047.24 | Core application + low-profile microservices. 100 GB EBS each.
3 | EKS Workers — High-Profile | r6g.2xlarge | 6 | 8 | 64 | 268.64 | 116.35 | 698.1 | Heavy microservices (billing, EMR, analytics). 200 GB EBS each.
4 | EBS for PVCs | gp3 3 TB | 1 | - | - | - | 438.26 | 438.26 | Persistent Volume Claims for stateful services.
5 | Jump Server (Bastion) | t3.medium | 1 | 2 | 4 | 33.87 | 17.66 | 17.66 | Secure SSH access. 20 GB SSD. Took t3.medium as t2.medium is not available in ap-south2
Additional AWS Services (from KareXpert BOM)
# | Service | Description | [5 empty] | Est $/mo | Notes
6 | S3 Object Storage | 10 TB Standard for backups, logs, files | [5 empty] | 256 | S3 Standard 10 TB.
7 | MongoDB Atlas M60 | 3-node replica (16 vCPU/64 GB/1 TB per node) | [5 empty] | 1800 | M60 tier via Marketplace. ⚠️ Check if replaces existing Atlas clusters or additional.
8 | WAF | 3M requests/mo, 3 rules | [5 empty] | 12 | Already in shared services — may be $0 incremental.
9 | ALB | Application Load Balancer | [5 empty] | 25 | 1 ALB for EKS ingress.
10 | Route 53 | DNS | [5 empty] | 6 | Already in shared services — may be $0 incremental.
11 | AWS Certificate Manager | Wildcard SSL | [5 empty] | 0 | Free for ACM public certs.
12 | AWS Inspector | EC2 scanning | [5 empty] | 0 | Already in shared Supporting Services.
13 | AWS ECR | Container image registry | [5 empty] | 15 | ~150 GB images × $0.10/GB.
14 | Security Services | SecurityHub+GuardDuty+KMS+Config+CloudWatch+SES | [5 empty] | 0 | ⚠️ OVERLAP — already in shared Supporting Services. $0 incremental.
| EKS + EC2 Compute (1 cluster + 24 workers + bastion, CSP 3yr) | [6 empty] | 2670.17
| Additional AWS Services | [6 empty] | 2098
| TOTAL KareXpert HIS Monthly Cost | [6 empty] | 4768.17
⚠️ IMPORTANT NOTES
1. All EC2 rates are ESTIMATES for ap-south-2 Graviton instances. Validate in AWS Pricing Calculator.
2. MongoDB Atlas M60 ($1,800/mo) — check if this REPLACES existing 3 Atlas clusters ($2,450) or is ADDITIONAL.
If replacement: net saving of $650/mo. If additional: +$1,800/mo.
3. Security/monitoring services already in shared Supporting Services — $0 incremental.
4. Total vCPU: 122 = 122 ¦ Total RAM: 964 = 964 GB ¦ 25 instances (1 EKS + 24 workers + 1 bastion)
5. EKS cluster fee ($73/mo) is NOT covered by Savings Plans — always full price.

## HIS BOM - MyHealthcare
MyHealthcare (MHEA) — AWS BOM Detail ¦ 1,000 CCU ¦ Primary: Hyderabad
Microservices on EC2 VMs (214 Graviton instances). All instances Linux/Graviton — available in ap-south-2.
# | Component | Instance Type | Qty | vCPU | RAM (GB) | EC2 OD $/mo ea | EC2 CSP 3yr ea | Total $/mo | Notes
1 | Compute Type 1 | c6g.large | 98 | 2 | 4 | 43.51 | 15.99 | 1567.02 | Stateless app microservices. Compute-optimised Graviton.
2 | Compute Type 2 | m6g.large | 24 | 2 | 8 | 51.76 | 18.76 | 450.24 | General-purpose microservices.
3 | Compute Type 3 | c6g.xlarge | 48 | 4 | 8 | 87.02 | 31.97 | 1534.56 | Mid-tier compute microservices.
4 | Compute Type 4 | m6g.xlarge | 36 | 4 | 16 | 103.51 | 37.52 | 1350.72 | Memory-balanced microservices.
5 | Compute Type 5 | m6g.2xlarge | 8 | 8 | 32 | 207.03 | 75.04 | 600.32 | Heavy workload services (reports, analytics).
Additional AWS Services (from MyHealthcare BOM)
# | Service | Description | [5 empty] | Est $/mo | Notes
6 | S3 Storage | Standard 20GB + Glacier Deep Archive 20GB | [5 empty] | 5 | Minimal storage — app data.
7 | CloudFront | CDN for patient-facing app | [5 empty] | 50 | Estimate based on 500 GB/mo transfer.
8 | API Gateway | REST API management | [5 empty] | 35 | Estimate based on 10M requests/mo.
9 | CloudWatch | Monitoring for 214 instances | [5 empty] | 150 | Already in shared services — may overlap.
10 | Cognito | User authentication (1000 CCU) | [5 empty] | 275 | 1000 MAU × $0.0055 + 50K auth events.
11 | Lambda | Serverless functions | [5 empty] | 20 | Event-driven processing.
12 | SES | Email notifications | [5 empty] | 10 | Transactional emails.
13 | SNS | Push notifications | [5 empty] | 5 | Mobile push + SMS.
14 | ALB | Application Load Balancer | [5 empty] | 25 | 1 ALB for HIS traffic. ⚠️ Check if shared ALBs cover this.
15 | VPC (2 S2S VPN + 5 IPv4) | Network + 5 public IPs | [5 empty] | 55 | VPN to branches. 5 EIPs × $3.60 + VPN.
16 | Network Firewall | AWS Network Firewall | [5 empty] | 175 | ⚠️ If Palo Alto covers this, remove.
17 | Security Services | Detective+Inspector+SecurityLake+SecurityHub+GuardDuty+WAF+Audit+Config+CloudTrail+IAM+KMS | [5 empty] | 0 | ⚠️ OVERLAP — already in shared Supporting Services. $0 incremental.
18 | X-Ray | Distributed tracing | [5 empty] | 15 | Trace analysis for microservices.
19 | Data Transfer | Intra-Region 2 TB/mo | [5 empty] | 30 | Within Hyderabad region.
| EC2 Compute (214 instances, CSP 3yr) | [6 empty] | 7532.62
| Additional AWS Services | [6 empty] | 850
| TOTAL MyHealthcare HIS Monthly Cost | [6 empty] | 8382.62
⚠️ IMPORTANT NOTES
1. All EC2 rates are ESTIMATES for ap-south-2 Graviton instances. Validate in AWS Pricing Calculator.
2. Security services (GuardDuty, Inspector, SecurityHub, WAF, Config, CloudTrail, KMS) = $0 incremental
because they are already in the shared Supporting Services sheet.
3. If Palo Alto covers Network Firewall functionality, remove the $175/mo line.
4. CloudWatch monitoring may overlap with shared services — validate.
5. Total vCPU: 644 ¦ Total RAM: 1800 GB ¦ 214 instances

## Active-Active vs Passive
DR Comparison: Active-Passive vs Active-Active (Chari Requested Both)
| DR Attribute | Active-Passive (Current Quote) | Active-Active (Optional) | Difference
| DR Instance Sizing | Pilot-light (smaller) | Full size (match prod) | +70% compute
| RPO (Recovery Point Objective) | < 1 hour | Near-zero
| RTO (Recovery Time Objective) | 30-60 minutes | < 5 minutes
| Traffic Distribution | Mumbai on failover only | Both regions serve | +100% compute
| Replication Mode | Continuous async | Synchronous critical DBs
| Monthly DR Cost (EC2 + Supporting) | 10587.5 | 13125.3 | 2537.8
| Annual DR Cost (EC2 + Supporting) | 127050 | 157503.6 | 30453.6
| Data Transfer | ~$60/mo | ~$200/mo | +$140/mo
| Operational Complexity | Simpler | Complex | Higher overhead
| Best Fit For | 30-min RTO tolerance | Zero-downtime critical
Active-Active DR Costing — Full Size Instances (Mumbai)
| Server | Instance (Full Size) | EC2 $/mo | EBS $/mo | Total $/mo
| RAINDC03 (DR) | m6i.xlarge | 208.43 | 18.24 | 226.67
| Rchbbserver (DR) | m6a.4xlarge | 2091.71 | 101.92 | 2193.63
| RCHAEON (DR) | r6a.4xlarge | 2141.7 | 160.16 | 2301.86
| Rainbow_MRD (DR) | c6a.8xlarge | 1359.01 | 1960.8 | 3319.81
| SAP_PI_PRD (DR) | m6a.4xlarge | 702.43 | 127.68 | 830.11
| repsapGRP (DR) | r6a.2xlarge | 429.1 | 218.88 | 647.98
| repsapAPP (DR) | r6a.2xlarge | 438.65 | 100.32 | 538.97
| RCHSOLMAN72 (DR) | r6a.2xlarge | 465.71 | 132.24 | 597.95
| RAINBOW80992 (DR) | m6a.2xlarge | 347.42 | 31.92 | 379.34
| mobileapp (DR) | m6a.4xlarge | 176.36 | 100.32 | 276.68
| TOTAL Active-Active DR (Full Size, CSP 3yr) |  |  |  | 11313
| Active-Active Supporting Services — Mumbai (Full Active Region) | Monthly (USD) | Annual (USD) | Notes
| Service | Monthly $ | Notes | Smaller instances, scale-up on failover
| Data Transfer Egress (Mumbai) | 303.25 | Active region serving internet traffic — combined intra+inbound+egress matches HYD active-region (PDF: $303.25) | Full production-size, always running
| Data Transfer Inter-Region | 176.13 | Bi-directional HYD↔Mumbai — set to AP-validated value as floor; actual AA cost may exceed this | Additional cost for Active-Active
| VPC + NAT Gateway (Mumbai) | 329.83 | Full HA NAT for active traffic (PDF-validated HYD: VPN + NAT Gateway $329.83)
| AWS Inspector (Mumbai) | 36.24 | Full scanning (PDF price)
| GuardDuty (Mumbai) | 244.6 | Full threat detection (PDF price)
| AWS Config (Mumbai) | 18.5 | Compliance monitoring
| Security Hub (Mumbai) | 85.01 | CSPM for active region (PDF-validated HYD: $85.01)
| CloudTrail (Mumbai) | 0.2 | Audit logging
| WAF (Mumbai) | 12.2 | Web protection for active traffic
| CloudWatch (Mumbai) | 84.28 | Full monitoring (PDF price)
| AWS Backup (Mumbai) | 391.78 | Full primary backup (matches HYD per PDF: $391.78). AP Mumbai DR backup is lower at $295.62 because it is CRR copy only.
| ELB 3x ALB (Mumbai) | 74.24 | Full load balancing (PDF price)
| S3 2TB (Mumbai) | 52.74 | Logs and storage (PDF price)
| KMS (Mumbai) | 3.3 | Encryption (PDF price)
| TOTAL Active-Active Supporting (Mumbai) | 1812.3
Complete DR Cost Comparison (EC2 + Supporting Services)
| Component | Active-Passive | Active-Active | Difference
| DR EC2 Instances | 8281.29 | 11313 | 3031.71
| DR Supporting Services | 2306.21 | 1812.3 | -493.91
| TOTAL DR Cost | 10587.5 | 13125.3 | 2537.8
Recommendation
Active-Passive (Recommended): Lower cost, simpler ops. 30-60 min RTO. DR instances are pilot-light (smaller), scale up on failover. DRS handles replication.
Active-Active: Full production-size instances in both regions. < 5 min RTO. Higher cost but near-zero downtime. No DRS needed (both regions active).
Hybrid option: Active-Active for clinical-critical (HIS, Biometric, Blood Bank) + Active-Passive for non-critical. Balance cost vs RTO requirements.
ℹ️ All prices aligned with AWS Pricing Calculator export (24-Apr-2026). AP = DR TCO sheet + DR supporting services. AA = full prod-size in Mumbai.

## Existing AWS HMS (Phase 2)
Existing AWS HMS Workloads — Phase 2 Migration to Hyderabad
S.No | Service | Resource | Instance/Config | OS | Region | Est $/mo | Notes
1 | EC2 | AAHISRPTSERV02-Prod-rep | m6a.2xlarge | Linux | Hyderabad | 104.32 | HMS Report Server 2. m6a.2xlarge Linux CSP 3yr NU. [Source: AWS Calculator ap-south-2, 250GB EBS]
2 | EC2 | AAINTFACESERV02-Prod | m6a.2xlarge | Linux | Hyderabad | 99.76 | Interface Server 2. m6a.2xlarge Linux CSP 3yr NU. [Source: AWS Calculator ap-south-2, 200GB EBS]
3 | EC2 | AAHISAPPSERV02-Prod | m6a.2xlarge | Linux | Hyderabad | 99.76 | HMS App Server 2. m6a.2xlarge Linux CSP 3yr NU. [Source: AWS Calculator ap-south-2, 200GB EBS]
4 | EC2 | AAHISAPPSERV03-Prod | m6a.2xlarge | Linux | Hyderabad | 99.76 | HMS App Server 3. m6a.2xlarge Linux CSP 3yr NU. [Source: AWS Calculator ap-south-2, 200GB EBS]
5 | EC2 | MIRTHDBSERV01-DR | m6a.large | Linux | Hyderabad | 130.87 | Mirth DR Server. m6a.large Linux CSP 3yr NU. [Source: AWS Calculator ap-south-2, 1TB EBS]
6 | EC2 | AAINTFACESERV01-Prod | m6a.2xlarge | Linux | Hyderabad | 99.76 | Interface Server 1. m6a.2xlarge Linux CSP 3yr NU. [Source: AWS Calculator ap-south-2, 200GB EBS]
7 | EC2 | AAHISAPPSERV01-Prod | m6a.2xlarge | Linux | Hyderabad | 99.76 | HMS App Server 1. m6a.2xlarge Linux CSP 3yr NU. [Source: AWS Calculator ap-south-2, 200GB EBS]
8 | EC2 | AAHISRPTSERV01-Prod-rep | m6a.2xlarge | Linux | Hyderabad | 99.76 | HMS Report Server 1. m6a.2xlarge Linux CSP 3yr NU. [Source: AWS Calculator ap-south-2, 200GB EBS]
9 | EC2 | MIRTHDBSERV01-Prod-1 | m6a.2xlarge | Linux | Hyderabad | 192.01 | Mirth Primary - CRITICAL HL7 broker. m6a.2xlarge Linux CSP 3yr NU. [Source: AWS Calculator ap-south-2, 1TB EBS]
10 | EC2 | DEPLOYSERV01 | t3.small (fixed) | Linux | Hyderabad | 10.87 | DEPLOYSERV01 t3.small OD 8hr/day, 180 GB. [Source: AWS Calculator 30-Apr-2026]
11 | EC2 | Grafana Monitoring | c6a.large | Linux | Hyderabad | 63.32 | Grafana c6a.large CSP 3yr No Upfront, 500 GB. [Source: AWS Calculator 30-Apr-2026]
12 | EC2 | newserver-26-08-2025 | t3.xlarge (fixed) | Windows | Hyderabad | 58.66 | Unknown server — confirm purpose with Chari. t3.xlarge Win OD 8hr/day. [Estimated: needs validation]
13 | EC2 | New-server-replica | t3.xlarge (fixed) | Windows | Hyderabad | 58.66 | Unknown replica. t3.xlarge Win OD 8hr/day. [Estimated: needs validation in AWS Calculator]
14 | Redshift | Analytics Cluster | 2x dc2.large | - | Hyderabad | 459.9 | Redshift Analytics. 2x dc2.large OnDemand. [Source: AWS Calculator ap-south-2]
15 | S3 | HMS Storage | 8 TB | - | Hyderabad | 657.89 | S3 Primary Storage 8TB. [Source: AWS Calculator ap-south-2 Hyderabad]
16 | RDS MySQL | rainbow-database | db.t4g.small, 60GB | - | Hyderabad | 56.77 | RDS MySQL db.t4g.small 60GB gp2. [Source: AWS Calculator ap-south-2]
17 | ELB | ALB + NLB | 1 ALB + 1 NLB | - | Hyderabad | 41.76 | ELB 1 ALB + 1 NLB. [Source: AWS Calculator ap-south-2 Hyderabad]
18 | AWS Glue | ETL | 2 DPUs | - | Hyderabad | 1.76 | AWS Glue ETL 2 DPUs. [Source: AWS Calculator ap-south-2]
19 | VPC | Data Transfer | 4 TB out + 16 TB intra | - | Hyderabad | 775.37 | VPC Data Transfer 4TB out + 16TB intra. [Source: AWS Calculator ap-south-2]
20 | GuardDuty | HMS Threat Detection | Various | - | Hyderabad | 224.4 | GuardDuty HMS Threat Detection. [Source: AWS Calculator ap-south-2]
21 | CloudWatch | HMS Monitoring | 320 metrics, 122 GB | - | Hyderabad | 179.04 | CloudWatch HMS 320 metrics, 122GB logs. [Source: AWS Calculator ap-south-2]
22 | AWS Backup | HMS Primary Backup | 3.5 TB, 7-day | - | Hyderabad | 235.38 | AWS Backup 3.5TB, 7-day retention. Replaces CommVault. [Source: AWS Calculator ap-south-2]
23 | AWS DRS | HMS DR Replication | 10 servers, 5TB, 30 disks | - | Mumbai | 951.78 | AWS DRS 10 servers, 5TB, 30 disks. Cross-region HYD→Mumbai. [Source: AWS Calculator ap-south-1]
24 | Redshift | Analytics Backup | Backup only | - | Mumbai | 25 | Redshift DR Backup only 1TB. [Source: AWS Calculator ap-south-1]
25 | S3 | CRR Replica | 8 TB | - | Mumbai | 657.89 | S3 Cross-Region Replica 8TB. [Source: AWS Calculator ap-south-1]
26 | RDS MySQL | CRR Replica | db.t4g.small | - | Mumbai | 81.59 | RDS MySQL Cross-Region Replica. [Source: AWS Calculator ap-south-1]
27 | ELB | DR Load Balancers | 1 ALB + 1 NLB | - | Mumbai | 41.76 | ELB DR 1 ALB + 1 NLB. [Source: AWS Calculator ap-south-1]
28 | GuardDuty | DR Threat Detection | Various | - | Mumbai | 224.4 | GuardDuty DR Threat Detection. [Source: AWS Calculator ap-south-1]
29 | CloudWatch | DR Monitoring | 100 metrics | - | 0 | 64.48 | CloudWatch DR 100 metrics. [Source: AWS Calculator ap-south-1]
30 | AWS Backup | Cross-Region Copy | 3.5 TB | - | Mumbai | 312.7 | AWS Backup Cross-Region Copy 3.5TB. [Source: AWS Calculator ap-south-1]
TOTAL Existing AWS HMS | [5 empty] | 6209.14
*Pricing yet to validate. Required Details Bill of AWS, will help here.

## AD & PACS Infrastructure (hidden)
Active Directory & PACS Infrastructure — Rainbow Hospitals
Updated: 25-Apr-2026 ¦ AD details from Narsima (AWS SA) ¦ PACS: Separate Managed AD domain
ARCHITECTURE: Dual AD — Self-managed (core) + AWS Managed AD (PACS)
KEY ARCHITECTURE DECISIONS
1. RAINDC03/02 (rainbow.local) stays in Primary TCO — serves HIS, SAP, Blood Bank, Biometric, all existing workloads. No changes.
2. New AWS Managed Microsoft AD (imaging.rainbow.local) created specifically for PACS — separate security boundary.
3. One-way forest trust: PACS domain trusts Rainbow domain → radiologists get SSO to PACS without separate login.
4. PACS ↔ HIS integration via HL7/Mirth Connect is network-level (TCP/IP) — not AD-dependent.
5. 25 branch AD servers stay on-premises — provide local auth, DNS, DHCP. Not migrated to AWS.
6. Amazon FSx (rainbow.local) replaces 12 TB branch file shares — domain-joined to RAINDC03/02.
7. FSx (imaging.rainbow.local) for PACS imaging storage — domain-joined to Managed AD.
8. Route 53 Resolver still required — forwards DNS for both domains + CtrlS trust.
9. DR: RAINDC03 DR (self-managed, Mumbai) + Managed AD multi-region replica (native, Mumbai) + FSx DR.
AD ENVIRONMENT SUMMARY (From Narsima — 25-Apr-2026)
Total AD Objects | 3,374 (users + computers)
Domain Structure | Single domain (rainbow.local)
Group Policy | GPO policies in place, not complex
DNS/DHCP | Core switch at most locations; 4 locations have DNS on local AD server
AD-Dependent Apps | LDAP configured for HIS (Hospital Information System)
Trust Relationships | Existing trust with CtrlS domain
Branch Connectivity | MPLS to CtrlS, AWS VPN tunnels already configured
File Share Storage | 20 TB total, 12 TB used (breakdown per location pending)
OS Upgrades Needed | 13 servers on Win 2016, 1 on Win 2012 R2 (EOL), 1 Eval license
BRANCH AD SERVER INVENTORY (25 Locations — On-Premises, NOT migrated to AWS)
S.No | Location | IP Address | Hostname | OS | Migration Strategy | DNS on Local Server? | Notes
1 | Secunderabad | 192.168.40.12 | RCHVKPSV03 | Win Server 2019 Std | Keep On-Prem | No | Current OS
2 | Kondapur OP | 192.168.30.12 | RCHMPSV01 | Win Server 2016 Std | Keep On-Prem | No | Upgrade 2016→2022
3 | Kondapur IP | 192.168.3.10 | RCHKPSV04 | Win Server 2016 Std | Keep On-Prem | No | Upgrade 2016→2022
4 | Malviya Nagar | 192.168.13.25 | RCHMNSV001 | Win Server 2012 R2 Std | Keep On-Prem | No | ⚠️ EOL — upgrade mandatory
5 | Rosewalk | 192.168.34.12 | RCHPPDSV01 | Win Server 2016 | Keep On-Prem | No | Upgrade 2016→2022
6 | Vizag Health City | 192.168.36.12 | RCHHCVSV01 | Win Server 2019 | Keep On-Prem | Yes | DNS on local AD
7 | Guindy | 192.168.25.21 | RCHGDYSV01 | Win Server 2016 | Keep On-Prem | No | Upgrade 2016→2022
8 | Hebbal | 192.168.37.13 | RCHHBBSV01 | Win Server 2019 | Keep On-Prem | No | Current OS
9 | Heart Institute | 192.168.32.12 | RCHBCHSV001 | Win Server 2016 | Keep On-Prem | Yes | DNS on local AD
10 | BG Road | 192.168.8.12 | RCHBGSV05 | Win Server 2016 Std | Keep On-Prem | No | Upgrade 2016→2022
11 | Hydernagar | 192.168.6.10 | RCHHNSV03 | Win Server 2016 Std | Keep On-Prem | No | Upgrade 2016→2022
12 | Currency Nagar | 192.168.5.12 | RCHCUVSV01 | Win Storage Server 2016 | Keep On-Prem | No | ⚠️ Storage Server — file share priority
13 | Marathahalli | 192.168.7.207 | RCHMHSV07 | Win Server 2016 Std | Keep On-Prem | No | Upgrade 2016→2022
14 | LB Nagar | 192.168.10.234 | RCHLBNSV01 | Win Server 2016 Std | Keep On-Prem | Yes | DNS on local AD
15 | Banjara Hills | 192.168.17.22 | RCHBHSV02 | Win Server 2016 Std | Keep On-Prem | No | Upgrade 2016→2022
16 | Sholinganallur | 192.168.45.12 | RCHSNCSV01 | Win Server 2022 Std | Keep On-Prem | No | Latest OS
17 | Himayatnagar | 192.168.51.7 | RCHHMNRSV01 | Win Server 2019 Std | Keep On-Prem | No | Current OS
18 | Sarjapur | 192.168.53.7 | RCHSRJPSV01 | Win Server 2019 Std | Keep On-Prem | No | Current OS
19 | Annanagar | 192.168.55.7 | RCHANCSV01 | Win Server 2019 Std | Keep On-Prem | No | Current OS
20 | Warangal | 192.168.58.9 | RCHWGLSV02 | Win Server 2022 Std | Keep On-Prem | No | Latest OS
21 | Guwahati | 192.168.60.11 | RCHPBGSV01 | Win Server 2022 Std | Keep On-Prem | No | Latest OS
22 | Rajahmundry | 192.168.63.6 | RCHRJYSV02 | Win Server 2022 Std | Keep On-Prem | Yes | DNS on local AD
23 | B'lore Electronic City | 192.168.66.9 | RCHECSV01 | Win Server 2022 Std Eval | Keep On-Prem | No | ⚠️ Eval license
24 | Hennur Clinic | 192.168.70.9 | RCHHNCSV01 | Win Server 2022 Std | Keep On-Prem | No | Latest OS
AWS SERVICES — AD & PACS INFRASTRUCTURE (Added to TCO)
S.No | Service | Region | Configuration | Hosting Env | Monthly $ (USD) | Annual $ (USD) | Notes
1 | AWS Managed AD (PACS) | Hyderabad | Standard — imaging.rainbow.local | AD Infrastructure | 134 | 1608 | Separate AD for PACS. 2 DCs auto-managed in 2 AZs.
2 | Managed AD DR Replica | Mumbai | Multi-region extension | AD Infrastructure | 85 | 1020 | Native replication to Mumbai. No manual DR setup.
3 | RSAT Management EC2 | Hyderabad | t3.small Win — GPO/user admin | AD Infrastructure | 17.52 | 210.24 | RSAT tools for Managed AD administration.
4 | Amazon FSx (core) | Hyderabad | Multi-AZ, 12 TB SSD, 256 MB/s | AD Infrastructure | 1920 | 23040 | Replaces 12 TB branch file shares. DFS namespaces.
5 | FSx DR Replica (core) | Mumbai | Single-AZ, 12 TB SSD | AD Infrastructure | 960 | 11520 | Cross-region async replication of 12 TB AD file shares to Mumbai.
6 | FSx (PACS imaging) | Hyderabad | Multi-AZ, 5 TB SSD (assumed) | AD Infrastructure | 800 | 9600 | ⚠️ DICOM imaging storage. Pending customer specs.
7 | Route 53 Resolver (In) | Hyderabad | 2 inbound endpoints | AD Infrastructure | 50 | 600 | Branch DNS → AWS resource resolution.
8 | Route 53 Resolver (Out) | Hyderabad | Outbound to CtrlS + both domains | AD Infrastructure | 50 | 600 | CtrlS trust + dual domain DNS forwarding.
9 | PACS App Server | Hyderabad | m6i.2xlarge (8v/32GB) assumed | AD Infrastructure | 324 | 3888 | ⚠️ Typical PACS server. Pending customer specs.
10 | PACS Archive (S3) | Hyderabad | S3 IT 5 TB (assumed) | AD Infrastructure | 115 | 1380 | ⚠️ PACS DICOM long-term archive (S3). Separate from the 12 TB AD file shares. Volume pending customer.
11 | Forest Trust Config | Hyderabad | One-way trust (PACS trusts Rainbow) | AD Infrastructure | 0 | 0 | Configuration only. No recurring cost.
| TOTAL — Confirmed Items Only |  |  |  | 3216.52 | 38598.24 | Excludes placeholder items pending customer specs
| TOTAL — All Items (incl. placeholders) |  |  |  | 4455.52 | 53466.24 | Includes PACS placeholders — refine after customer confirmation

## Draft (hidden)
Server | Source (GB) | Disk Util % | Used (GB) | New EBS (GB) | Rationale
SAP_PI_PRD_New | 1150 | 90.09% | ~1,036 | 1400 | Highest active util. 1036/0.70 = 1,480 → rounded to 1,400
RCHSOLMAN72 | 1250 | 86.54% | ~1,082 | 1450 | 1082/0.70 = 1,546 → rounded to 1,450
RCHECCDEC | 1946 | 85.71% | ~1,668 | 2250 | 1668/0.70 = 2,383 → rounded to 2,250
sapgst | 730 | 84.76% | ~619 | 850 | 619/0.70 = 884 → rounded to 850
SAP_PI_DEV_New | 800 | 81.59% | ~653 | 900 | Just above 80%, small buffer added
SAP-DevTesting | 1100 | 80.74% | ~888 | 1200 | At 80% threshold, small buffer
BIUAT-MIS | 150 | 80.25% | ~120 | 180 | Small disk, small buffer (~30 GB)
Servers with disk utilization ≥ 85%: Increased EBS to bring the target steady-state utilization down to approximately 70%. The formula used: New EBS = Current Used Data / 0.70
Servers with disk utilization 80-85%: Small buffer added (rounding up to nearest 50-100 GB) since they're approaching the threshold but not critical yet.
Servers with disk utilization < 80%: Kept at source allocation or rounded up minimally.
Servers with no utilization data: Kept at source allocation — no justification to change without data.
Why 70% Target?
This is an industry-standard best practice for production storage:
OS/application overhead: Windows needs 10-15% free for updates, page files, temp files, crash dumps
Database growth buffer: SQL Server and HANA need free space for transaction logs, tempdb growth, index rebuilds
Alert threshold: Most monitoring tools trigger warnings at 80% and critical at 90%. Sizing at 70% gives a ~10% buffer before alerts fire.
EBS expansion window: While EBS gp3 can be expanded online, the cooldown period is 6 hours between modifications. If disk hits 95% during a batch job, you need pre-existing headroom.